## Slide 1
Task 1: Dashboard Creation (UofSC and BMW)
  UofSC and BMW to meet and discuss requirements and related tasks for dashboards
Task 2: Forecasting Model (UofSC)
  Refinement (Months 7-9)
  Validation based on feedback (Months 10-12)
Task 3: MPA Integration (Fraunhofer)
  Months 7-9
  Milestone 1: Delivery of AI material planner framework with integrated AI forecasting model ready for testing by users
Task 4: Material Planner with Visual Alerting and Recommendations (Fraunhofer)
  Months 10-12
  Milestone 2: Delivery of operational MPA

## Slide 2: Task 1: Dashboard Development (TBD)
Duration:
Deliverable:
Aim:
Sub activities:
Milestone:
What is needed from BMW:
What is needed from UofSC:
What is needed from Fraunhofer:

## Slide 3: Task 2: Forecasting Model
Duration: Jan-May 2022 (Months 7-12)
Deliverable: Parts forecasting model ready to be integrated into AI MPA
Aim: Refine, test and validate parts forecasting model developed in Phase 1
Sub activities: (preliminary list)
  Test and validate parts forecasting with historical data
  Test and validate optimized parameters for parts ordering
  Refine model as needed
Milestone 1: March 31, 2022; Refined forecasting model ready for user testing
Milestone 2: May 31, 2022; Refined and validated forecasting model based on user feedback
What is needed from BMW:
What is needed from Fraunhofer:

## Slide 4: Task 3: MPA integration
Duration: Jan-March 2022 (Months 7-9)
Deliverable: AI material planner framework with integrated AI forecasting model
Aim: Develop and deliver an operational MPA ‘alpha’ version at the end of the task, that selected end users and the developers can use together during the task 2 efforts.
Sub activities: (preliminary list)
  Develop real-time data access in the Azure Cloud.
  Continued knowledge transfer from BMW material planners for further developing knowledge and data relations
  Enable Dashboard replacement of md04 and material master values for what-if analysis
  Host mpa/assist web service
  Create a regression test service
  Elaborate parts forecasting model requirements, input and output
  Create integration plan, and integrate forecasting model with AI Material Planner
  Test forecasting model and AI Material Planner framework
  Update system based on testing result
Milestone 1: March 31, 2022; Delivery of AI material planner framework with integrated AI forecasting model
What is needed from BMW:
What is needed from UofSC:

## Slide 5: Task 4: AI Material Planner with Visual Alerting and Recommendations
Duration: April-June 2022 (Months 10-12)
Deliverable: Running Material Planner Assistant
Aim: validate, further develop, and tune the ‘alpha’ version of MPA into an operational product ready to use by material planners.
Sub activities: (preliminary list)
  Workshops with stakeholders
  Further elaborate alerting functionality and human readable action steps
  Work together with BMW on testing and validation
  Implement necessary changes in MPA
  Determine MPA operational rules, including rule revisions by BMW
Milestone: May 31, 2022; Delivery of the operational MPA
Milestone: June 30, 2022; Production utilization
What is needed from BMW:
What is needed from UofSC:

## Slide 6: Discussion Points with BMW
Defining dashboard requirements
  What platform, how will users login (browser?)
Confirming data source – is it Logan Prepared with tables materialmaster and md04_all